## BRAP
Buffer Recovery Action Plan
| Date | Delivery Name | Buffer used | % Critical Chain Complete | Needed Action | Assigned to… | Added to schedule (Y/N) | Date Complete | Notes

## BRAP Sample
Buffer Recovery Action Plan
| Date | Delivery Name | Buffer used | % Critical Chain Complete | Needed Action | Assigned to… | Added to schedule (Y/N) | Date Complete | Notes
2019-01-05
|  | Prototype ready | 15% | 12% | Talk with Contracts regarding our place in the lab queue. | William Lawry | Y | 2019-01-09 | We are having some difficulty in getting results back from the external lab.
[5 empty] | Research other lab options. | Jennifer Smith |  | 2019-01-08
|  | Product on market | 7% | 6% | (same)
2019-01-12
|  | Prototype ready | 18% | 15% | Bring manufacturing manager on board and explore options. | William Lawry |  |  | We made good progress with the lab, but had to add extra work to accommodate different types of results. Our main option to recover buffer currently seems to be in getting manufacturing to be more involved before the product design is complete.
|  | Product on market | 8% | 7%